## Sheet1
project plan
sprint# | task name | responsible | days | start | end | status
1 | Design header | mahmoud sobh | 5 | 2018-10-03 | 15-3-2018 | completed
1 | Design footer | mohamed ezat | 5 | 2018-10-03 | 15-3-2018 | completed
1 | Design slider | youstina | 7 | 15-3-2018 | 22-3-2018 | in progress
1 | Design registration page | mariam samy | 10 | 15-3-2018 | 25-3-2018 | in progress
2 | Design singers page | mahmoud sobh | 7 | 25-3-2018 | 2018-01-04 | not started
2 | Design songs page | mohamed ezat | 7 | 25-3-2018 | 2018-01-04 | not started
2 | Sign up | youstina | 10 | 27-3-2018 | 2018-04-04 | not started
2 | Log in | mariam samy | 10 | 27-3-2018 | 2018-04-04 | not started
3 | View the singers | mahmoud sobh | 7 | 2018-04-04 | 2018-11-04 | not started
3 | View of all songs for the singer | mohamed ezat | 10 | 2018-04-04 | 14-4-2018 | not started
3 | test project fatures | youstina | 5 | 2018-11-04 | 16-4-2018 | not started
3 | Choose one song to play | mariam samy | 7 | 2018-11-04 | 18-4-2018 | not started
4 | Play the song that has mp3 extension | mahmoud sobh | 14 | 2018-12-04 | 26-4-2018 | not started
4 | Search about song | mohamed ezat | 5 | 15-4-2018 | 20-4-2018 | not started
4 | test project fatures | youstina | 5 | 14-4-2018 | 19-4-2018 | not started
4 | test project fatures | mariam samy | 5 | 16-4-2018 | 21-4-2018 | not started